## Loop Check Sheet
LOOP CHECK / FUNCTIONAL TEST SHEET
LOOP IDENTIFICATION
| Loop / Tag No |  | Project / Plant Area
| Loop Description |  | Date of Test
| P&ID Reference |  | Signal Type
| Tested By |  | Witnessed By
CHECKLIST
| # | Check | Result | Value / Reading | Remarks | Initials
| 1 | Loop drawing and P&ID match the installed configuration
| 2 | Field instrument tag plate matches the loop schedule
| 3 | Cable route, glanding and termination inspected — no damage
| 4 | Screen / shield earthed at one point only (no ground loop)
| 5 | Loop wiring continuity verified end to end
| 6 | Insulation resistance test on signal cable acceptable
| 7 | Loop power supply voltage measured at field device (≥ minimum required)
| 8 | Polarity confirmed correct at transmitter and at input card
| 9 | Transmitter range / LRV & URV configured as per instrument index
| 10 | Damping value set as specified
| 11 | NAMUR NE43 fault action configured (upscale / downscale as specified)
| 12 | 0% signal injected — DCS/PLC reading correct
| 13 | 25% signal injected — DCS/PLC reading correct
| 14 | 50% signal injected — DCS/PLC reading correct
| 15 | 75% signal injected — DCS/PLC reading correct
| 16 | 100% signal injected — DCS/PLC reading correct
| 17 | Engineering units and decimal places correct on operator display
| 18 | Alarm setpoints configured and annunciation verified
| 19 | Trip / interlock action verified (where applicable)
| 20 | Final element (valve / motor) stroked and response confirmed
| 21 | Loop returned to normal service and left in correct mode
| 22 | Punch list items recorded and communicated
SUMMARY
|  | Checks passed | 0
|  | Checks failed | 0
|  | Not applicable | 0
|  | Outstanding (not yet checked) | 22
|  | LOOP ACCEPTED | INCOMPLETE
Free loop check sheet from Quantum Volt — quantum-volt.com This is one sheet from the Calibration & Loop Check Management Pack: an instrument register with automatic due dates, a compliance dashboard, five-point calibration certificates with as-found/as-left analysis, reference standard control, a competency matrix, an OOT investigation record and a 9-page written procedure. Questions or to order: akhand.singh@akhandnow.com